## Slide 1: Release Wave 3: go/no-go preparation
Steering Committee pre-read, readiness as of 9 October 2026
Cut-over weekend 21 to 22 November | decision meeting 6 November
Prepared with the Transformation Cockpit prototype
Notes: Pre-read for the go/no-go preparation checkpoint (T-3 weeks per the readiness framework). Everything in this deck traces to a row in the cockpit data folder.

## Slide 2: Five dimensions amber, one red: recommendation is a conditional go
Amber
D1 Data quality and reconciliation
Reconciliation 99.1% vs 99.5% target; 2 open S2 data defects; 2 of 3 mock runs done
Green
D2 Client and advisor communication
100% clients notified; 96% advisors briefed; hypercare model published
Amber
D3 Training and enablement
Training 88% vs 95%; 12 of 14 floorwalkers; procedures 94% published
Amber
D4 Technology cut-over and decommissioning
DR1 margin 1h15 vs 2h target; rollback partially tested; DEF-209 open
Amber
D5 Regulatory, risk and control sign-off
Op Risk approval forecast 13 Nov; controls tested 90%; retention plan agreed
Red
D6 Operational capacity and service continuity
Hypercare staffing 86% of model (50 of 58 FTE); 120% load test not yet run
Rule applied: red in D6 only, which is not a critical dimension (D1, D4, D5). A conditional go requires a SteerCo-approved mitigation for D6, tracked daily, and owners plus closure dates for every amber before cut-over. Source: readiness_kpis.csv, framework section 4.
Notes: Dimension RAG is the worst criterion, no averaging. D6 is red on staffing; D1, D4, D5 are amber and under control with dates. D2 is green.

## Slide 3: Three inputs to the decision paper now land after the paper is due
Today
9 Oct
Mock 3
(was 10 Oct)
17 Oct
Batch fix deployed
(was 16 Oct)
23 Oct
Decision paper due
4 Nov
Go/no-go SteerCo
6 Nov
DR2 + rollback
(was 31 Oct)
8 Nov
Op Risk approval
(was 30 Oct)
13 Nov
Final confirmation
18 Nov
Cut-over
21 Nov
Dress rehearsal 2 (7 to 8 Nov)
One day after the SteerCo. Rollback is only partially tested until then. The committee decides on DR1 evidence plus fix test results, or defers one week.
Operational Risk approval (13 Nov)
Op Risk will not sign off while DEF-121 (312 records, manual enrichment, no owner yet) is open. A conditional approval needs the Head of Op Risk at the meeting.
Network change freeze (1 Dec)
28 to 29 Nov is the only fallback weekend. Any later deferral moves go-live to January.
Source: milestone_plan.xlsx (M02, M20, M22, M26), weekly updates wk41. Red markers: forecast after the decision paper. Orange: slipped but before it. Timeline not to scale.
Notes: The cockpit flags seven dependency conflicts. The three that matter for the decision are DR2, Op Risk approval and the competence assessment, all forecast after the decision paper is issued on 4 Nov.

## Slide 4: Three risks drive the recommendation; each is owned and dated
R03
Hypercare staffing below model
50 of 58 FTE confirmed. Service centre teams carry year-end volumes in the same window. Service partner needs four weeks' notice.
Severity / likelihood High / High
Owner Operations Readiness Lead
Mitigation due 23 Oct
R02
Op Risk approval after the SteerCo
Close DEF-114 by 16 Oct (fix in test). Assign an owner to DEF-121 enrichment this week. Ask for conditional approval in person.
Severity / likelihood High / High
Owner Risk and Control Lead
Mitigation due 6 Nov
R01
Batch fix late for DR2
Fix passed unit tests; regression from 12 Oct; deployment 23 Oct confirmed in the change calendar. Fallback: DR2 on current build, weaker evidence.
Severity / likelihood High / Medium
Owner Platform Engineering Lead
Mitigation due 23 Oct
Source: raid_log.csv, ranked by severity and likelihood. Full register of 24 items in the cockpit, Schedule tab.
Notes: R03 is what makes D6 red. R02 is the one that can turn the recommendation into a no-go if Op Risk will not attend. R01 is improving.

## Slide 5: Decision requested: close the hypercare staffing gap by 23 October
Option A | Recommended
Contract 8 temporary FTE from the service partner for three weeks
Cost about CHF 180,000. Lifts staffing to 100% of model. Needs sign-off by 23 Oct (four weeks' notice). Keeps full day-one scope.
Option B
Defer the corporate actions module to a December release
No cost. Reduces day-one volume so 50 FTE meets the reduced model. Adds a second cut-over inside the change freeze window, which needs its own approval.
Option C
Hybrid: 4 partner FTE plus corporate actions deferred by two weeks
About CHF 90,000. Requested by the chair for comparison. Same freeze-window exposure as B, smaller.
Conditions attached to a conditional go, whichever option is chosen
Owner named for DEF-121 enrichment by 16 Oct; DEF-114 closed by 16 Oct (D1).
Protected training slots held on 20 to 21 Oct; 95% completion by 10 Nov; two Operations floorwalkers released with the staffing decision (D3).
Batch fix deployed 23 Oct; DR2 with end-to-end rollback on 7 to 8 Nov; committee reconvenes by email on 9 Nov to confirm (D4).
Head of Operational Risk attends on 6 Nov to give or refuse a conditional approval; written retention confirmation by 16 Oct (D5).
Notes: The committee is asked to choose A, B or C and to accept the four conditions. Without a choice by 23 Oct, option A is no longer available and D6 stays red into the 6 Nov meeting.

## Slide 6: How this pre-read was produced, and what we measured
Transformation Cockpit prototype
1
Ingest
Milestone plan (xlsx), RAID log, readiness KPIs, free-text weekly updates
2
Analyse, no AI
Slips, dependency conflicts, unowned items, deterministic RAG scoring against framework thresholds
3
Propose, with AI
Weekly updates read for risks, slips, decisions. Each proposal quotes its source sentence. A reviewer accepts or rejects
4
Draft and release
Executive report and talking points generated with a source tag on every line. DRAFT until a named reviewer releases
What we measured
95%
recall on the 10 updates the rules were written next to
17%
recall on 5 held-out updates in a different writing style
Keyword rules are precise (97 to 100%) but blind to new phrasing. That is the case for an LLM extractor with the same two controls: quoted source sentence, human review of every proposal. The LLM engine is built and not yet measured.
Effort estimate, to be validated
About 5 hours per week of manual reading and report compilation today; about 1 hour with the cockpit, if the extractor reaches 85% recall on real updates. Assumptions in 02_Evaluation_Report.md.
Next steps
Measure the LLM engine on the held-out set; second labeller for agreement
Two-week trial on anonymised real updates with a PMO analyst reviewing
Decide on entry into the weekly reporting cycle only after that
Notes: Closing: the tool is a draft assistant with controls, not a decision maker. The honest evaluation number is 17%, and the next step is to measure the LLM engine the same way.