## Milestones
id | workstream | milestone | owner | baseline_date | forecast_date | status | pct_complete | depends_on
M01 | PMO | Release 3 scope baseline approved | Program Manager | 2026-06-26 | 2026-06-26 | Complete | 100
M02 | PMO | Go/no-go decision paper issued | PMO Lead | 2026-11-04 | 2026-11-04 | On track | 35 | M12;M18;M22;M26
M03 | PMO | Go/no-go SteerCo | Program Sponsor | 2026-11-06 | 2026-11-06 | On track | 0 | M02
M04 | PMO | Final confirmation (T-3 days) | Program Sponsor | 2026-11-18 | 2026-11-18 | Not started | 0 | M03
M05 | PMO | Cut-over weekend | Technology Delivery Lead | 2026-11-21 | 2026-11-21 | Not started | 0 | M04
M06 | Data Migration | Reference data mapping sign-off | Data Migration Lead | 2026-09-11 | 2026-09-25 | Complete | 100
M07 | Data Migration | Mock migration 2 | Data Migration Lead | 2026-09-19 | 2026-09-19 | Complete | 100
M08 | Data Migration | Mock migration 3 | Data Migration Lead | 2026-10-10 | 2026-10-17 | At risk | 60 | M07;M21
M09 | Data Migration | Severity 1/2 data defects closed | Data Migration Lead | 2026-10-30 | 2026-11-06 | Delayed | 40 | M08
M10 | Data Migration | Reconciliation sign-off by Finance | Finance Controller | 2026-11-13 | 2026-11-13 | Not started | 0 | M09
M11 | Business Change | Client notification letters dispatched | Business Change Lead | 2026-09-26 | 2026-09-26 | Complete | 100
M12 | Business Change | Advisor briefings completed (all desks) | Business Change Lead | 2026-10-16 | 2026-10-16 | On track | 92
M13 | Business Change | Hypercare contact model published | Business Change Lead | 2026-10-02 | 2026-10-02 | Complete | 100
M14 | Training | Release 3 training content published | Learning Lead | 2026-09-12 | 2026-09-12 | Complete | 100
M15 | Training | Training environment refreshed with mock 2 data | Technology Delivery Lead | 2026-09-26 | 2026-10-03 | Complete | 100 | M07
M16 | Training | Mandatory training 95% complete | Learning Lead | 2026-10-30 | 2026-11-10 | Delayed | 88 | M15
M17 | Training | Floorwalker roster confirmed | Learning Lead | 2026-10-23 | 2026-10-23 | At risk | 55 | M28
M18 | Training | Competence assessment closed | Learning Lead | 2026-11-06 | 2026-11-06 | On track | 30 | M16
M19 | Technology | Dress rehearsal 1 | Technology Delivery Lead | 2026-10-03 | 2026-10-04 | Complete | 100
M20 | Technology | Dress rehearsal 2 | Technology Delivery Lead | 2026-10-31 | 2026-11-07 | At risk | 10 | M19;M21
M21 | Technology | Batch window performance fix deployed | Platform Engineering Lead | 2026-10-16 | 2026-10-23 | Delayed | 45
M22 | Technology | Rollback procedure tested end to end | Technology Delivery Lead | 2026-10-31 | 2026-11-07 | At risk | 50 | M20
M23 | Technology | Legacy archiving and access-removal plan approved | Decommissioning Lead | 2026-10-23 | 2026-10-23 | On track | 85
M24 | Risk & Control | Key control testing on target platform | Risk and Control Lead | 2026-10-23 | 2026-10-23 | On track | 90 | M20
M25 | Risk & Control | Compliance approval | Compliance Officer | 2026-10-30 | 2026-10-30 | On track | 50 | M24
M26 | Risk & Control | Operational risk approval | Operational Risk Officer | 2026-10-30 | 2026-11-13 | Delayed | 20 | M24;M09
M27 | Risk & Control | Record retention confirmation | Records Management | 2026-10-16 | 2026-10-16 | On track | 75 | M23
M28 | Operations | Hypercare staffing plan approved | Operations Readiness Lead | 2026-10-09 | 2026-10-23 | Delayed | 60
M29 | Operations | Load test at 120% of expected peak | Platform Engineering Lead | 2026-10-16 | 2026-10-23 | At risk | 30 | M21
M30 | Operations | BCP update walkthrough | Operations Readiness Lead | 2026-10-30 | 2026-10-30 | On track | 40

## Meta
key | value
as_of | 2026-10-09
program | Program HORIZON (fictional)
release | Release Wave 3
cutover_weekend | 2026-11-21
go_no_go_steerco | 2026-11-06